## Tasks
Task ID | Task | WP | Personnel | Start | Length | Start1 | Length1 | Start2 | Length2 | Start3 | Length3 | Start4 | Length4 | Start5 | Length5 | FS Dependency | Milestone | M Month | MS Task ID | Deliverable | D Month | D Task ID
1 | task1 | 1 | PDRA1 | 0 | 2 | [11 empty] | ex1 | 2 | 1
2 | task2 | 1 | PDRA1 | 2 | 3 | [10 empty] | [1] | ex2 | 6 | 2
3 | task3 | 1 | PDRA1 | 5 | 3 | [10 empty] | [1] | ex3 | 8 | 3
4 | task4 | 1 | PDRA1 | 8 | 5 | [14 empty] | Product | 13 | 4
5 | task5 | 1 | PDRA1 | 17 | 0.25 | 23 | 0.25 | 30 | 0.25 | 35.5 | 0.25
6 | task6 | 1 | PDRA1/PhD | 8 | 34 | [10 empty] | [1]
7 | task7 | 1 | PhD | 0 | 8
8 | task8 | 1 | PhD | 8 | 14
9 | task9 | 1 | PhD | 22 | 14
10 | task10 | 1 | PhD | 36 | 6
11 | task11 | 2 | PDRA2 | 6 | 9 | [10 empty] | [1]
12 | task12 | 2 | PDRA2 | 15 | 9 | [10 empty] | [11]
13 | task13 | 2 | PDRA2 | 24 | 18 | [10 empty] | [12]
14 | task14 | 3 | RJB | 3 | 3
15 | task15 | 3 | RJB | 8 | 3
16 | task16 | 3 | PDRA1 | 13 | 5 | 24 | 0.3 | 33 | 0.3
17 | task17 | 3 | PDRA1 | 18 | 4
18 | task18 | 3 | PDRA1 | 22 | 2 | [10 empty] | [17]
19 | task19 | 3 | PDRA1 | 24 | 5 | [10 empty] | [14,15,16]
20 | task20 | 3 | PDRA1 | 29 | 2 | [10 empty] | [19]
21 | task21 | 3 | PDRA1 & 2 | 31 | 5 | [10 empty] | [18,19]
22 | task22 | 3 | PDRA2 | 36 | 6 | [10 empty] | [21]
23
24
25
26
27
28
29
30
31
Note on A1: Microsoft Office User: This is the task ID only used for dependancy at the moment
Note on B1: Kevin Critchley: Insert task description. Do not leave any empty lines as it messes up the indexing. (will try to fix this in the future)
Note on C1: Kevin Critchley: This is the work package. These values can be removed from the gantt. They can be any string
Note on D1: Kevin Critchley: Add the personal doing the Task.
Note on E1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The length is the time the task takes in months
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: if you have some think that is repeated you can add more 'start' and 'length' columns
Note on G1: Kevin Critchley: add as many starts and lengths as you wish by adding columns in pairs as shown. This allows taks to start and stop
Note on Q1: Kevin Critchley: Please a the requirement for a task to start after a task is complete by entering the task IDs (col A) that need to be complete in a comma separated list in square brackets.
Note on R1: Kevin Critchley: Add milestones.
Note on S1: Kevin Critchley: Add the month that the milestone is predicted to be met
Note on T1: Microsoft Office User: This controls which task the MS is associated with. Enter the Task ID from col A
Note on U1: Kevin Critchley: Same as milestone
Note on V1: Kevin Critchley: Same as milestone
Note on W1: Microsoft Office User: Add the assocaited Task ID (they do not have to be unique)